APPENDIX F - WORK PLAN

STRATEGIC GROWTH COUNCIL/Department of Conservation– Sustainable Communities Planning Grant Award

Grantee:   City of San Diego        Grant Number: 3014-624

Jurisdiction:  City of San Diego     Department: Planning

Project Title: Balboa Avenue Station Area Plan

| High Level Activities/Milestones (with Deliverables and Indicators) | Responsible Parties | Timetable in months (Start year: 2015) |
| --- | --- | --- |
| Project Contracting Finalize Scope of Work for Consultant Team Consultant Procurement Process Deliverables: Scope of Work; Request for Proposal; Consultant Contract; Meeting Notes | City, SANDAG, CirculateSD, Consultant Team | Month One to Month Three |
| Project Administration & Management Bi-Monthly Coordination Meetings Project Schedule & Management Quarterly Invoices & Reports Grant Close Out Deliverables: Meeting Notes; Project Schedule; Progress Reports; Invoices | City, SANDAG, CirculateSD, Consultant Team | Duration of the Plan – Thirty-six months Month Thirty-Four to Month Thirty-Six |
| Community Outreach & Participation Outreach & Participation Plan Community Outreach Workshops Community Planning Group Updates Multi-modal Mobility Survey Walk Audit Online Communications Development Deliverables: Outreach & Participation Plan; Workshops, Notices, Summaries, Materials; Communtiy Planning Group Updates; Presentation Materials; Multi-modal Mobility Survey; Walk Audit; Online Materials and Useage Data | City, SANDAG, CirculateSD, Consultant Team | Duration of the Plan – Thirty-six months |
| Existing Conditions Analysis, Opprtunities & Constraints Environmental Reconnaissance Land Use Assessment Market Assessment Multi-modal Mobility Assessment Deliverables: Existing Conditions technical memos, report; Maps | City, SANDAG, Consultant Team | Month Three to Month Seven |
| Urban Design and Land Use Analysis Opportunities and Constraints Mapping Urban Design Vision Land Use Scenarios Multi-modal Land Use Scenario Evaluation Preferred Land Use Deliverables: Opportunities and Constraints Mapping; Urban Design Visioning Report & Graphics; 2 Land Use Scenarios; Maps, GIS Data; Evaluation Matrix/Report; Preferred Land Use; Illustrations | City, SANDAG, Consultant Team | Month Seven to Month Eleven |
| Economic Feasibility Analysis Market Analysis Financial Feasibility Financing Strategies Fiscal Impact Analyses Deliverables: Draft technical memos, reports; Pro-formas | City, Consultant Team | Month Eleven to Month Fourteen |
| Multi-Modal Mobility Study Future travel forecasting Mobility Concept Development and Initial Vetting (multi-modal access to transit) Future Conditions Analysis with Mobility Concept Plan Transportation Impact Analysis as Needed Deliverables: Draft technical memos; Analysis Report; Mobility Recommendations, feasibility analysis, concept plan and drawings; Project list with detailed cost estimates. | City, SANDAG, Consultant Team | Month Fourteen to Month Seventeen |
| Environmental Analysis Prepare Technical Studies Prepare of CEQA Document Screenchecks Prepare Draft and Final CEQA Document Deliverables: Technical studies and anlaysis; Draft & Final Environmental Document | City, Consultant Team | Month Seventeen to Month Thirty-three |
| Draft & Final Station Area Plan Community Plan Amendments, Rezone, Facilities Financing Plan Amendments Specific Plan Implementation Plan Deliverables: Draft & Final Community Plan Amendment, Facilities Financing Plan, Zoning Map, Specific Plan, Implementation Plan | City, SANDAG, Consultant Team | Month Thirty-Two to Month Thirty-Six |